GOAL I:

To create processes and protocols whereby the Council identifies, analyzes, and consistently incorporates TK and LK, and the social science of TK and LK, into Council decision-making processes to support the use of best available scientific information in EBFM.

- Objective 1:  Over the next 2-3 years the TF will identify and define sources of L&TK, and social science of L&TK, to support the use of best scientific information available in Council decision-making.

Protocols will address both discrete actions and broader Council processes

  - Come to consensus on definitions of terms (TK, LK, Subsistence, protocol, etc.)

  - If no sources of L&TK/socsci are known on the issue being examined (e.g. ‘sculpins’), note this as a significant data gap; perhaps identify individuals/communities/organizations that could assist in filling that gap; perhaps develop potential research questions and methods that could be used to fill that gap and add them to the Council’s list of research priorities/questions.

  - Write up a briefing discussing the benefits of incorporating these types of knowledge into Council decision-making

  - Explore and document what protocols and projects already exist that are similar/related to what the TF is trying to do

  - Explore potential synergies among projects (e.g. SASAP, ongoing ANO projects, etc.) and between Action Modules.

  - Develop a publically available collection of resources, groups, and research labs as to provide practitioners with easy access to relevant information on LK/TK/Subsistence. ... (to put on website?)

Q: Who will maintain/curate?

Q: Where will it be housed?

  - Develop a suggested reading list

- Objective 2: The TF will provide guidance and analytical protocols to council staff on how to evaluate and analyze L&TK, and the social science of L&TK.

Protocols will address both discrete actions and broader Council processes

Criterial for council staff

Tasks

  - Write guidance document

- Including criteria for evaluating L&TK/social science sources

  - Develop analytical protocol

- Objective 3: The TF will provide guidance on how T&LK and the social science of T&LK should be incorporated into Council decision-making processes.

  - Develop synthesize information

  - Detail process by which information from L&TK/socsci can be considered and integrated along with other sources of information (e.g. from western fisheries biology) in Council decision-making and processes.

  - Identify appropriate and meaningful pathways/onramps where information can enter into the process.

  - Identify potential sources and other avenues of information

  - Establish protocols to gain permission/consent to use information

  - Establish protocols for recognition of knowledge sources (citation guide?)

Goal II

To create clear direction(s) for the Council regarding how impacts to subsistence are defined and incorporated into analyses as well as mitigation strategies for potential impacts to subsistence resources or uses of those resources.

- Objective 4: Over the next 2-3 years the TF will identify sources of subsistence information.

  - Facilitate strong partnerships among council staff and subsistence users

  - Clarify characteristics of subsistence (have a discussion re: Ak native users and other sub. users) for the purpose of the TF

  - Conduct knowledge gap/unaccounted for info

  - Examine the Council decision-making processes relate subsistence use to ID relevant onrampa

  - Develop document of existing subsistence documents/projects/resources

  - Include ethical guidelines to inform Council decision-making processes

- Objectve 5: The TF will provide guidance on how subsistence information can be incorporated into Council decision-making processes.

- including current assessment models

- E.g.: Reporting diretly to council through NMFS (Mike Williams)

- Objective 6: Identify existing measures and potential opportunities to mitigate impacts to sub. resources and subsistence resources users.

- E.g.: cod fisheries and king salmon

- Identify possible onroads for consideration of impacts to subsistence resources and sub, users.

- Develop Roadmap for the Council.